## Sheet1
Name | RollNo | Role | Sprints | Tasks
Ch.Kavyasri | 24211A6716 | Product Owner, Scrum Master | Sprint 1 | Gather requirements from Client
Create Product Backlog
Sprint Planning
Conduct Daily Standups
Update Client
|  |  | Sprint 2 | Sprint Planning Meeting
Update Client
Sprint Progress Tracking
Sprint Review Meeting
|  |  | Sprint 3 | Track Sprint Progress
Coordinate Team Tasks
Sprint Review
|  |  | Sprint 4 | Track Sprint Progress
Manage Team Issues
Sprint Review
|  |  | Sprint 5 | Prioritize Remaining Backlog
Track Sprint Progress
Sprint Review
|  |  | Sprint 6 | Coordinate Deployment Activities
Track Sprint Progress
Sprint Review
|  |  | Sprint 7 | Final Project Presentation
Project Closure Activities
Final Review
A.Manasa | 24211A6702 | Lead Devloper | Sprint 1 | Create project architecture
Define coding standards
Create GitHub branch strategy
|  |  | Sprint 2 | Design HR Management Page
Design Employee Management Page
Design Asset Management Page
Design Asset Inventory Page
|  |  | Sprint 3 | Design Asset Request Page
Design Request Approval Page
Design Asset Assignment Page
|  |  | Sprint 4 | Design Inventory Management Page
Design Maintenance Management Page
Design Asset Return Page
|  |  | Sprint 5 | Design Dashboard Page
Design Reports Page
|  |  | Sprint 6 | Support Deployment Activities
Support Application Configuration
|  |  | Sprint 7 | Resolve Remaining Bugs
Perform Final Code Review
B.Shravan Kumar | 24211A6708 | Frontend Developer | Sprint 1 | Design Home Page
Design Login and Registration UI
|  |  | Sprint 2 | Develop HR Management Functionality
Develop Employee Management Functionality
Develop Asset Management Functionality
Develop Asset Search Functionality
|  |  | Sprint 3 | Develop Asset Request Functionality
Develop Request Approval Functionality
Develop Asset Assignment Functionality
|  |  | Sprint 4 | Develop Inventory Management Functionality
Develop Maintenance Functionality
Develop Asset Return Functionality
|  |  | Sprint 5 | Develop Dashboard Functionality
Develop Reports Functionality
|  |  | Sprint 6 | Fix User Interface Issues
Verify Frontend Deployment
|  |  | Sprint 7 | Fix User Interface Bugs
Perform Final UI Verification
A.Meghana | 24211A6701 | Backend Developer | Sprint 1 | Design Database
Create User Authentication APIs
Registration API
Login API
Forgot Password API
|  |  | Sprint 2 | Create Employee Database Tables
Create Asset Database Tables
Manage Employee Records
Manage Asset Records
|  |  | Sprint 3 | Create Asset Request Database Tables
Create Asset Assignment Database Tables
Maintain Asset Assignment Records
|  |  | Sprint 4 | Create Maintenance Database Tables
Store Maintenance and Repair Records
Manage Asset Return Records
|  |  | Sprint 5 | Create Report Queries
Manage Report Data
|  |  | Sprint 6 | Support Database Deployment
Configure Database Backup Process
|  |  | Sprint 7 | Optimize Database Performance
Verify Database Backup Process
K.Satwika | 24211A6757 | QA Engineer | Sprint 1 | Prepare Test Plan
Create Test Cases for Login and Registration
|  |  | Sprint 2 | Test Employee Management Features
Test Asset Management Features
Test Asset Search Functionality
Identify and Report Bugs
Retest Fixed Issues
|  |  | Sprint 3 | Test Asset Request Features
Test Asset Assignment Features
Identify and Report Bugs
Retest Fixed Issues
|  |  | Sprint 4 | Test Inventory Management Features
Test Maintenance Features
Test Asset Return Features
Identify and Report Bugs
Retest Fixed Issues
|  |  | Sprint 5 | Test Dashboard Features
Test Reports Features
Identify and Report Bugs
Retest Fixed Issues
|  |  | Sprint 6 | Perform Integration Testing
Verify Deployment Results
Report Issues and Defects
|  |  | Sprint 7 | Perform Final System Testing
Conduct User Acceptance Testing (UAT)
Verify All Bug Fixes
Ch.Gopinath | 24211A6718 | DevOps Engineer | Sprint 1 | Create GitHub repository
Setup Git workflow
Setup CI basics
|  |  | Sprint 2 | Manage GitHub Branches
Support Code Merging Activities
Verify Application Builds
|  |  | Sprint 3 | Support Code Integration
Verify Application Builds
|  |  | Sprint 4 | Maintain Source Code Repository
Verify Application Builds
|  |  | Sprint 5 | Verify Application Builds
Support Deployment Activities
|  |  | Sprint 6 | Configure Jenkins Pipeline
Implement CI/CD Process
|  |  | Sprint 7 | Configure Prometheus Monitoring
Configure Grafana Dashboards
Monitor Application Performance
Ch.Pooja | 24211A6719 | Backend DevOps | Sprint 1 | Install Docker
Learn Kubernetes basics
Create Docker learning notes
|  |  | Sprint 2 | Dockerize backend application
Docker configuration Updates
|  |  | Sprint 3 | Dockerize frontend
Multi-container setup
Docker Image Updates
|  |  | Sprint 4 | Docker Compose setup
Container networking
Docker Service Configuration
|  |  | Sprint 5 | Learn Kubernetes deployments
Create Deployment YAML files
Docker Configuration Enhancement
|  |  | Sprint 6 | Kubernetes Deployment
Services and Ingress
Deploy Frontend and Backend
Docker Containerization
|  |  | Sprint 7 | Prometheus Monitoring
Grafana Dashboard Setup

## Sheet2
Sprint Backlog and Product Backlog are properly aligned.
Sprints | PB | Tasks
Sprint 1 | PB-01 | User Authentication
| PB-02 | Role-Based Access Control
| PB-23 | Database Design
| PB-24 | API Development
| PB-25 | Frontend Development
| PB-27 | GitHub Repository Setup
Sprint 2 | PB-03 | Add Asset
| PB-04 | Update Asset
| PB-05 | Delete/Retire Asset
| PB-06 | Asset Inventory View
| PB-20 | Search Assets
Sprint 3 | PB-07 | Asset Assignment
| PB-08 | Asset Reassignment
| PB-09 | Track Asset Ownership
| PB-13 | Asset Return Request
| PB-15 | Admin Dashboard
Sprint 4 | PB-10 | Issue Reporting
| PB-11 | Maintenance Request Management
| PB-12 | Repair History Tracking
| PB-14 | Technician Dashboard
| PB-21 | Notification System
Sprint 5 | PB-16 | Inventory Reports
| PB-17 | Assigned Asset Reports
| PB-18 | Maintenance Reports
| PB-19 | Retired Asset Reports
| PB-22 | Audit Logs
Sprint 6 | PB-26 | Unit Testing
| PB-28 | Jenkins CI/CD Pipeline
| PB-29 | Docker Containerization
| PB-30 | Kubernetes Deployment
Sprint 7 | PB-31 | Prometheus Monitoring
| PB-32 | Grafana Dashboard
| PB-33 | Documentation