## 🏃 Team Eta
Team Gamma · IT Asset Management System
Methodology: Scrum ¦ Sprint Length: 2 Weeks ¦ Total Sprints: 7 ¦ Duration: Jul–Oct 2026 ¦ Members: 7
👥 TEAM ROSTER
# | Member Name | Role | Email | Sprint Focus | Pts/Sprint | Availability | Status
1 | Ch.Kavyasri | Product Owner & Scrum Master | 24211a6716@bvrit.ac.in | Backlog & Client Updates | 10 | 100% | Active
2 | A.Manasa | Lead Developer | 24211a6702@bvrit.ac.in | Architecture & Integration | 12 | 100% | Active
3 | B.Shravan Kumar | Frontend Developer | 24211a6708@bvrit.ac.in | UI Development | 10 | 100% | Active
4 | Ch.Gopinath | DevOps Engineer | 24211a6718@bvrit.ac.in | GitHub, Jenkins, CI/CD | 10 | 100% | Active
5 | K.Satwika | QA Engineer | 24211a6757@bvrit.ac.in | Testing & QA | 12 | 100% | Active
6 | A.Meghana | Backend Developer | 24211a6701@bvrit.ac.in | APIs & Database | 12 | 100% | Active
7 | Ch.pooja | DevOps (Docker/K8s | 24211a6719@bvrit.ac.in | Docker & Kubernetes | 12 | 100% | Active
📅 SPRINT PLAN — 10 SPRINTS
Sprint # | Sprint Goal | Start Date | End Date | Duration | Committed Pts | Completed Pts | % Done | Velocity | Defects Found | Defects Fixed | Carry Over | Status | Review Date | Retro Date | Notes
Sprint 1 | Project Setup & User Management | 05 Jan 2026 | 18 Jan 2026 | 14 days | 77 | 77 | 100% | 77 | 3 | 3 | 0 | Completed | 19 Jan 2026 | 20 Jan 2026 | Delivered ✓
Sprint 2 | Authentication & User Roles | 19 Jan 2026 | 01 Feb 2026 | 14 days | 81 | 78 | 96.3% | 78 | 4 | 3 | 3 | Completed | 02 Feb 2026 | 03 Feb 2026 | Delivered ✓
Sprint 3 | Asset Management | 02 Feb 2026 | 15 Feb 2026 | 14 days | 85 | 79 | 92.94% | 79 | 5 | 5 | 6 | Completed | 16 Feb 2026 | 17 Feb 2026 | Delivered ✓
Sprint 4 | Asset Request & Assignment | 16 Feb 2026 | 01 Mar 2026 | 14 days | 77 | 46 | 59.74% | 46 | 2 | 1 | 31 | In Progress | 02 Mar 2026 | 03 Mar 2026 | Running…
Sprint 5 | Maintenance & Reports | 02 Mar 2026 | 15 Mar 2026 | 14 days | 81 | 0 | 0% |  | 0 | 0 | 81 | Planned | 16 Mar 2026 | 17 Mar 2026 | —
Sprint 6 | CI/CD, Docker & Kubernetes | 16 Mar 2026 | 29 Mar 2026 | 14 days | 85 | 0 | 0% |  | 0 | 0 | 85 | Planned | 30 Mar 2026 | 31 Mar 2026 | —
Sprint 7 | Monitoring & Final Delivery | 30 Mar 2026 | 12 Apr 2026 | 14 days | 77 | 0 | 0% |  | 0 | 0 | 77 | Planned | 13 Apr 2026 | 14 Apr 2026 | —
[9 empty] | 0 | 0 | 0 | Planned | 27 Apr 2026 | 28 Apr 2026 | —
[9 empty] | 0 | 0 | 0 | Planned | 11 May 2026 | 12 May 2026 | —
[9 empty] | 0 | 0 | 0 | Planned | 25 May 2026 | 26 May 2026 | —
TOTALS |  |  |  |  | 563 | 280 | 49.85% | 70 | 14 | 12 | 283
🔄 DAILY STAND-UP LOG (Current Sprint)
Member | Role | Yesterday's Work | Today's Plan | Blockers | Story Pts | Task Status | Help Needed?
Student 1 | PO/SM | Backlog created | Sprint planning | None | 3 | Done | No
Student 2 | Lead Dev | Architecture design | Module integration | None | 5 | In Progress | No
Student 3 | DevOps | GitHub setup | Jenkins setup | None | 4 | In Progress | No
Student 4 | QA | Test cases written | Execute tests | None | 3 | In Progress | No
Student 5 | Backend | DB schema | Authentication APIs | None | 6 | In Progress | No
Student 6 | DevOps | Docker installed | Create Dockerfiles | None | 5 | In Progress | No
Student 7 | Frontend | Login UI | Dashboard UI | None | 5 | In Progress | No
📈 SPRINT METRICS & BURN-DOWN SUMMARY
Sprint | Committed | Completed | Remaining | Velocity | % Done | Defects | Fix Rate
Sprint 1 | 77 | 77 | 0 | 77 | 100% | 3 | 3
Sprint 2 | 81 | 78 | 3 | 78 | 96.3% | 4 | 3
Sprint 3 | 85 | 79 | 6 | 79 | 92.94% | 5 | 5
Sprint 4 | 77 | 46 | 31 | 46 | 59.74% | 2 | 1
Sprint 5 | 81 | 0 | 81 |  | 0% | 0 | 0
Sprint 6 | 85 | 0 | 85 |  | 0% | 0 | 0
Sprint 7 | 77 | 0 | 77 |  | 0% | 0 | 0