## Sheet1
Name | RollNo | Role | Sprints | Tasks | Estimated time
Ch.Kavyasri | 24211A6716 | Product Owner, Scrum Master | Sprint 1 | Gather requirements from client
Create Product Backlog
Sprint Planning
Conduct Daily Standups
Update client
|  |  | Sprint 2 | Review progress
Manage sprint tasks
Demo login module to client
|  |  | Sprint 3 | Review asset management requirements
Sprint review meeting
|  |  | Sprint 4 | Gather feedback from client
|  |  | Sprint 5 | Prioritize remaining backlog
|  |  | Sprint 6 | Coordinate deployment activities
|  |  | Sprint 7 | Final Project Presentation
Sprint Closure Report
A.Manasa | 24211A6702 | Lead Devloper | Sprint 1 | Create project architecture
Define coding standards
Create GitHub branch strategy
|  |  | Sprint 2 | Integrate frontend and backend
|  |  | Sprint 3 | Asset module integration
|  |  | Sprint 4 | Review code quality
Help team members
|  |  | Sprint 5 | Integrate reporting module
|  |  | Sprint 6 | Fix production issues
|  |  | Sprint 7 | Final code review
B.Shravan kumar | 24211A6716 | Frontend Developer | Sprint1 | Design Home Page
Design Login and Registration UI
|  |  | Sprint 2 | Login Page
Registration Page
Forgot Password Page
|  |  | Sprint 3 | Asset Management UI
|  |  | Sprint 4 | Request Page
Approval Page
Assignment UI
|  |  | Sprint 5 | Maintenance Dashboard
Reports UI
|  |  | Sprint 6 | UI fixes after deployment
|  |  | Sptint 7 | User Manual
UI Documentation
Ch.Gopinath | 24211A6718 | DevOps Engineer | Sprint 1 | Create GitHub repository
Setup Git workflow
Setup CI basics
|  |  | Sprint 2 | Configure GitHub Actions/Jenkins basics
|  |  | Sprint 3 | Build automation setup
|  |  | Sprint 4 | Improve Jenkins pipeline
|  |  | Sprint 5 | Automated testing in pipeline
|  |  | Sprint 6 | Jenkins Pipeline
CI/CD Automation
Docker Hub Integration
|  |  | Sprint 7 | Docker Hub Integration
Alert configuration
K.Satwika | 24211A6757 | QA Engineer | Sprint 1 | Prepare Test Plan
Create Test Cases for Login and Registration
|  |  | Sprint 2 | Test Login and Registration
Report bugs
|  |  | Sprint 3 | Test asset operations
update to team leader or client
|  |  | Sprint 4 | Test request and approval flow
helping frontend developer
|  |  | Sprint 5 | Test maintenance workflow
Regression testing
|  |  | Sprint 6 | End-to-End Testing
|  |  | Sprint 7 | Final Testing Report
A.Meghana | 24211A6701 | Backend Engineer | Sprint 1 | Design Database
Create User Authentication APIs
|  |  | Sprint 2 | Registration API
Login API
Forgot Password API
|  |  | Sprint 3 | Add Asset
Delete Asset
Update Asset
Search Asset APIs
|  |  | Sprint 4 | Asset Request API
Approval API
Assignment API
|  |  | Sprint 5 | Maintenance APIs
Reports APIs
|  |  | Sprint 6 | Deploy Backend
Support CI/CD
|  |  | Sprint 7 | API Documentation
Backend Documentation
Ch.Pooja | 24211A6719 | DevOps (Docker/Kubernetes) | Sprint 1 | Install Docker
Learn Kubernetes basics
Create Docker learning notes
|  |  | Sprint 2 | Dockerize backend application
|  |  | Sprint 3 | Dockerize frontend
Multi-container setup
|  |  | Sprint4 | Docker Compose setup
Container networking
|  |  | Sprint 5 | Learn Kubernetes deployments
Create Deployment YAML files
|  |  | Sprint 6 | Kubernetes Deployment
Services and Ingress
Deploy Frontend and Backend
|  |  | Sprint 7 | Grafana Dashboard
Kubernetes Monitoring